## Backlog
Task | Epic | Estimate | Actual hours | Status | Weight | Help onboard | Help return | Debt | Helps me
Intro help | Intro UX | 3 |  | ToDo | 0.75 | Yes | Yes | Yes | No
List all testing scenarios | QA | 1 | 3 | Done | 0.75 | Yes | Yes | Yes | No
Debug Safari | Tech Debt | 2 |  | ToDo | 0.75 | Yes | Yes | Yes | No
Adjust account totals | New Day UX | 1 |  | ToDo | 0.5 | No | Yes | No | Yes
Ledger History UX | New Day UX | 1 |  | ToDo | 0.5 | No | Yes | No | Yes
Mark as complete/incomplete in Ledger | New Day UX | 1 |  | ToDo | 0.5 | No | Yes | No | Yes
Mobile UX | Clean UX | 1 |  | ToDo | 0.5 | Yes | No | Yes | No
Daily notifications | Retention | 5 |  | ToDo | 0.5 | No | Yes | No | Yes
Code cleanup | Tech Debt | 1 |  | ToDo | 0.5 | No | No | Yes | Yes
Cookie consent | Cookie consent | 1 |  | ToDo | 0.25 | No | No | Yes | No
Searchable tables | Searchable tables | 3 |  | ToDo | 0.25 | No | No | No | Yes
Chart adjustments | Clean UX | 1 |  | ToDo | 0.25 | No | No | No | Yes
Holidays | Validity | 1 |  | ToDo | 0.25 | No | No | Yes | No
Last day of month | Validity | 1 |  | ToDo | 0.25 | No | No | Yes | No
Undo/Redo | Undo | 2 |  | ToDo | 0.25 | No | No | No | Yes
Date Picker UX | Clean UX | 1 |  | ToDo | 0.25 | No | No | No | Yes
Loading | Clean UX | 1 |  | ToDo | 0.25 | No | No | Yes | No
Export and Import | Undo | 3 |  | ToDo | 0.25 | No | No | No | Yes
Create new experiment | Undo | 3 |  | ToDo | 0 | No | No | No | No

## Test Checklist
| Test | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-25 | 2020-04-30 | 2020-05-07
TEST_1000 | With Blank Datastore open Proximo | PASS | PASS | PASS | PASS | PASS | PASS
| Test: Don't see blinking/flashing pages/elements | PASS | PASS | PASS | PASS | PASS | PASS
| Test: Welcome page opened | PASS | PASS | PASS | PASS | PASS | PASS
TEST_1150 | With TEST_1000 Add three transactions on the Welcome page: 1, 150, Wage 15, 200, Wage 5, -300, Rent | PASS | PASS | PASS | PASS | PASS | PASS
| Test: Land on Dashboard | PASS | PASS | PASS | PASS | PASS | PASS
| Test: Intro is shown |  |  | PASS | PASS | PASS | PASS
| Click "Skip" to close intro |  |  | PASS | PASS | PASS | PASS
| Test: Line Chart is not blank and showing one growing sine wave-like line | FAIL | PASS | PASS | PASS | PASS | PASS
| Test: Account Ending Balance is 600 | FAIL | PASS | PASS | PASS | PASS | PASS
| Test: Account Initial Balance is 0 | FAIL | PASS | PASS | PASS | PASS | PASS
| Open Ledger | SKEPT | PASS | PASS | PASS | PASS | PASS
| Test: Ledger is not empty and showing transactions | SKEPT | PASS | PASS | PASS | PASS | PASS
| Open Schedule | SKEPT | PASS | PASS | PASS | PASS | PASS
| Test: Schedule is not empty and showing three schedules on one account | SKEPT | PASS | PASS | PASS | PASS | PASS
| Open Developer Console |  |  |  | PASS | PASS | PASS
| Test: Developer Console does not contain any error messages |  |  |  | PASS | PASS | PASS
TEST_1300 | With TEST_1150 Modify Rent transaction by changing its value to -400 Open Dashboard |  | PASS | PASS | PASS | PASS | PASS
| Test: Line Chart is not blank and showing one falling sine wave-like line |  | PASS | PASS | PASS | PASS | PASS
| Test: Account Ending Balance is -600 |  | PASS | PASS | PASS | PASS | PASS
| Test: Account Summary table is RED |  | PASS | PASS | PASS | PASS | PASS
| Open Ledger |  | PASS | PASS | PASS | PASS | PASS
| Test: All Rent transactions have been updated with the new value of -400 |  | PASS | PASS | PASS | PASS | PASS
| Test: All Rent transactions are RED |  | PASS | PASS | PASS | PASS | PASS
| Test: Bottom half of the ledger is RED |  | PASS | PASS | PASS | PASS | PASS
| Open Developer Console |  |  |  | PASS | PASS | PASS
| Test: Developer Console does not contain any error messages |  |  |  | PASS | PASS | PASS
TEST_1450 | With TEST_1300 Delete 1, 150, Wage Modify 15, 200, Wage by changing its schedule to Weekly on Mondays Open Dashboard |  | PASS | PASS | PASS | PASS | PASS
| Test: Line Chart is not blank and showing one line |  | PASS | PASS | PASS | PASS | PASS
| Test: Account Ending Balance is 5600 |  | PASS | PASS | PASS | PASS | PASS
| Test: Account Summary table is WHITE |  | PASS | PASS | PASS | PASS | PASS
| Open Ledger |  | PASS | PASS | PASS | PASS | PASS
| Test: Wage transactions happen only once every Monday and have a value of 200 |  | PASS | PASS | PASS | PASS | PASS
| Test: Entire ledger table is WHITE |  | PASS | PASS | PASS | PASS | PASS
| Open Developer Console |  |  |  | PASS | PASS | PASS
| Test: Developer Console does not contain any error messages |  |  |  | PASS | PASS | PASS
LAST | With a non-blank datastore Switch to Schedule Delete all transactions |  | PASS | PASS | PASS | PASS | PASS
| Test: Welcome screen is opened |  | PASS | PASS | PASS | PASS | PASS
| Test: Dashboard, Schedule, and Ledger tabs are disabled |  | PASS | PASS | PASS | PASS | PASS
| Open Developer Console |  |  |  | PASS | PASS | PASS
| Test: Developer Console does not contain any error messages |  |  |  | PASS | PASS | PASS
TEST_2000 | With TEST_1300 Update version of any single intro messages to the next number (previous max + 1) |  |  | PASS | PASS | PASS | PASS
| Refresh proximo and navigate to the page that contains the updated message |  |  | PASS | PASS | PASS | PASS
| Test: Proximo shows the intro message with the update version number (and only one message is shown without next/previous pages) |  |  | PASS | PASS | PASS | PASS
| Click outside of the message to make it disappear |  |  | PASS | PASS | PASS | PASS
| Switch to a different page and return back |  |  | PASS | PASS | PASS | PASS
| Test: Proximo shows the intro message with the update version number (and only one message is shown without next/previous pages) |  |  | PASS | PASS | PASS | PASS
| Click "done" |  |  | PASS | PASS | PASS | PASS
| Switch to a different page and return back |  |  | PASS | PASS | PASS | PASS
| Test: Proximo is not showing any intro messages |  |  | PASS | PASS | PASS | PASS
| Refresh proximo and navigate to the page that contains the updated message |  |  | PASS | PASS | PASS | PASS
| Test: Proximo is not showing any intro messages |  |  | PASS | PASS | PASS | PASS
TEST_2150 | With TEST_2000 Update version of all intro messages in dashboard.ts to the next number (previous max + 1) |  |  |  | PASS | PASS | PASS
| Refresh proximo and navigate to the dashboard |  |  |  | PASS | PASS | PASS
| Test: Proximo shows the intro consisting of all of the updated messages |  |  |  | PASS | PASS | PASS
| Test: The last intro page highlights the "Schedule" tab button |  |  |  | PASS | PASS | PASS
| Click on "Schedule" tab button |  |  |  | PASS | PASS | PASS
| Switch back to the dashboard |  |  |  | PASS | PASS | PASS
| Test: Proximo is not showing any intro messages |  |  |  | PASS | PASS | PASS
| Refresh proximo and navigate to the dashboard |  |  |  | PASS | PASS | PASS
| Test: Proximo is not showing any intro messages |  |  |  | PASS | PASS | PASS
| Open Developer Console and filter on "intro-building-context" events |  |  |  | PASS | PASS | PASS
| Test: versionCompleted parameter of the dashboard container should match the version set earlier in this test |  |  |  | PASS | PASS | PASS
| Test: versionCompleted parameter of all other containers should be greater than 0 |  |  |  | PASS | PASS | PASS